## Sprint 1 Plan
User Story | Task | Estimated Hours | Actual Hours | To Do
US1: As a project manager, I need to establish the version control foundation so that all code changes can be tracked and managed effectively.​ | T1.1: Initialize GitHub Repository​ | 2 | 3 | Done
- Create a new public repository on GitHub named ProjectRobot1_2025. - Initialize the repository with a README.mdfile containing the project title and basic description. - Clone the remote repository to the local machine. - Create and switch to a dedicated development branch (e.g., dev-main).
US2: As a developer, I need a detailed iteration plan so that the project has a clear roadmap and measurable tasks for the upcoming sprints.​ | T2.1: Define Sprint Plans​ | 3 | 3.5 | Done
- In the Sprint 1 Plansheet, define the goal and detailed tasks for the current sprint. - Create Sprint 2 Planand Sprint 3 Plansheets with clear objectives and user stories. - Break down each user story into actionable tasks with time estimates for all sprints.
US3: As a team member, I need to visualize progress through a burndown chart so that we can monitor the sprint's health and maintain a sustainable pace.​ | T3.1: Setup Burndown Chart​ | 2 | 2.5 | Done
- Create a new worksheet named Burndown Chart. - Set up columns: Date, Ideal Remaining (Hours), Actual Remaining (Hours). - Calculate and input the ideal burndown trend based on the total estimated effort
US4: As a hardware engineer, I need the physical robot assembled and ready so that it can be used for software testing and demonstration in the next sprint.​ | ​​T4.1: Assemble Robot Platform​ | 4 | 3.5 | Done
- Unbox the Micro:bit robot kit and verify all components against the packing list. - Assemble the chassis, attach the wheels and universal wheel. - Install the battery pack and ensure all mechanical connections are secure.

## Sprint 2 Plan
User Story | Task | Estimated Hours | Actual Hours | Status
US1: As a developer, I want to create a python script to let the robot move in multiple directions.​ | ​​T1.1: Implement Direction Control Logic​- Code forward, backward, left, and right movements in direction_control.py. - Test each direction to ensure the robot responds correctly. - Display corresponding arrows on the Micro:bit LED during movement. | 3 | 3.5 | Done
​​US2: As a developer, I want to create a python script to let the robot move with user defined speeds.​ | T2.1: Implement Speed Control Logic​ - Design a speed control function in speed_control.pyaccepting user-defined values. - Implement PWM control for smooth acceleration and deceleration. - Test different speed levels (e.g., 50, 100, 150, 200) for stability. | 3 | 2.5 | Done
US3: As a developer, I want to create a python script to let the robot move, following user defined path.​ | T3.1: Implement Path Control Logic​- Design path sequences (e.g., square, circle, 'L' shape) in path_control.py. - Program button interactions (A/B) for path selection and execution. - Integrate and test the complete path-following functionality. ​ | 4 | 5 | Done
| ​T3.2: System Integration & Final Testing​- Ensure all scripts (move_car.py, direction_control.py, speed_control.py, path_control.py) work together. - Conduct comprehensive final tests of all robotic functions. | 2 | 2 | Done

## Sprint 3 Plan
User Story | Task | Estimated Hours | Actual Hours | Status
​​US1: As a student, I want to write a comprehensive project report.​ | T1.1: Compile Main Project Report​- Write and format Parts 1-4 of the final project report. - Integrate all screenshots, charts, and code listings. - Review and proofread the complete document. | 5 | 6 | Done
​​US2: As a developer, I want to record and upload a demonstration video.​ | T2.1: Record and Edit Demo Video​- Plan and script the 5-minute video demonstration. - Record robot functionality and verbal explanation. - Edit the video and upload it to Bilibili/BaiduPan. | 3 | 3 | Done
US3: As a learner, I want to complete the CDP and Socio-Technical Analysis report.​ | ​​T3.1: Write Socio-Technical Analysis Report​- Complete the report based on the provided template. | 3 | 2.5 | Done
| ​​T3.2: Write Career Development Plan (CDP)​ | 2 | 2 | Done
- Reflect on personal learning and future career goals

## Burndown Chart1
Sprint 1 date | ideal Remaining Work（hours） | Actual Remaining Work（hours）
Day 1 (Start)​ | 11 | 11
Day 1 (End)​ | 5.5 | 6
Day 2(End)​ | 0 | 0
​

## Burndown Chart2
Sprint 2 date | ideal Remaining Work（hours） | Actual Remaining Work（hours）
Day 1 (Start)​ | 12 | 12
Day 1 (End)​ | 8 | 8.5
Day 2(End)​ | 4 | 4
Day 3(End)​ | 0 | 0

## Burndown Chart 3
Sprint 3 date | ideal Remaining Work（hours） | Actual Remaining Work（hours）
Day 1 (Start)​ | 13 | 13
Day 1 (End)​ | 6.5 | 7
Day 2(End)​ | 0 | 0
​